## Project Planner
Rancor Project Planner
Start Date January 20th, 2022. End Date February 20th, 2022 | [10 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ASSIGNED TO (Secondary) | COMPLETED BY (Supporter) | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | TIME ALLOTMENT (% Planned) | PERIODS
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
All | Roger(All) | Group Formation | 1 | 1 | 1 | 1 | 100%
All | Roger (All) | API Selection | 1 | 15 | 1 | 24 | 160%
Monica | Monica | API Confirmation | 22 | 1 | 27 | 1 | 100%
All | All | Workflow Process Implementation | 1 | 31 | 1 | 27 | 87.1%
Chad | Chad | Repo Set Up | 23 | 2 | 25 | 2 | 100%
Chad | Chad (All) | File Configuration | 23 | 2 | 25 | 2 | 100%
All | All | Tool Selection (CI, Rstudio) | 23 | 2 | 24 | 2 | 100%
Roger | Roger | Workflow Commencement | 23 | 1 | 25 | 1 | 100%
Chad | Chad | License | 23 | 1 | 25 | 1 | 100%
Chad | Chad | Description | 24 | 1 | 25 | 1 | 100%
Chad | Chad (Roger) | Namespace management | 24 | 7 | 26 | 6 | 85.71%
Monica | Monica (All) | Code of Conduct | 24 | 1 | 27 | 1 | 100%
Monica | Monica (All) | Contribution | 26 | 1 | 27 | 1 | 100%
Roger | Roger | Function 1 (People) Code | 26 | 5 | 26 | 2 | 40%
Roger | Chad | Function 1 Testcode | 27 | 4 | 31 | 1 | 25%
Roger | Roger | Function 1 Documentation | 28 | 2 | 30 | 2 | 100%
Chad | Roger | Function 2 (Planet) Code | 26 | 3 | 28 | 3 | 100%
Chad | Chad | Function 2 Testcode | 27 | 3 | 31 | 1 | 33.33%
Chad | All | Function 2 Documentation | 28 | 2 | 30 | 2 | 100%
Monica | Chad | Function 3 (Starship) Code | 26 | 5 | 28 | 3 | 60%
Monica | Chad | Function 3 Testcode | 27 | 4 | 31 | 1 | 25%
Monica | Chad | Function 3 Documentation | 28 | 3 | 29 | 3 | 100%
Roger | Chad | Function 4 (Vehicles) Code | 27 | 3 | 28 | 2 | 66.67%
Roger | Chad | Function 4 Testcode | 28 | 3 | 31 | 1 | 33.33%
Roger | Chad | Function 4 Documentation | 29 | 2 | 29 | 2 | 100%
Chad | Monica | Function 5 (Species) Code | 27 | 2 | 27 | 3 | 150%
Chad | Chad | Function 5 Testcode | 28 | 2 | 31 | 1 | 50%
Monica | Monica | Function 5 Documentation | 29 | 2 | 30 | 2 | 100%
Tentative | Monica | Function 6 (Film) Code | 29 | 1 | 30 | 1 | 100%
Tentative | Chad | Function 6 Testcode | 30 | 1 | 30 | 1 | 100%
Tentative | Monica | Function 6 Documentation | 31 | 1 | 30 | 1 | 100%
Monica | Monica (Chad) | README | 29 | 3 | 30 | 2 | 66.67%
Monica | Chad | Vignette | 30 | 2 | 31 | 1 | 50%
Monica | All | Final Review | 31 | 2 | 31 | 2 | 100%
Monica | Monica | Go Live (Submission) | 32 | 1 |  |  | 0%
Tentative |  | CRAN publication | 32 | 1 |  |  | 0%
Roger | Roger | Ruling the Galactic Empire | 1 | 31 | 1 | 31 | 100%
Chad | Chad | Software Trouble Shooting | 1 | 31 | 1 | 31 | 100%
Monica | Monica | Documentation Oversight | 25 | 7 | 25 | 7 | 100%